## Compliance Matrix
Requirement ID | Title | Category | Verification Method | Verification Status | Observed Value / Evidence Excerpt | Evidence Document Ref | Verdict
REQ-AUT-001 | Cell Overvoltage Detection & Contactor Trip | High-Voltage Battery | Test / Inspection | COMPLETE | Overvoltage injected at 4.255 V; persistent for 100 ms triggered contactor trip in 14.2 ms. Verdict: PASS. | 08_BMS_Functional_Safety_Validation_Report.pdf | PASS
REQ-AUT-002 | HV Pack Operating Voltage Range | High-Voltage Battery | Test / Inspection | COMPLETE | Validated continuous pack monitoring from 380.0 V DC to 820.0 V DC across full operational span. Verdict: PASS. | 08_BMS_Functional_Safety_Validation_Report.pdf | PASS
REQ-AUT-003 | Cell Operating Temperature Operating Envelope | High-Voltage Battery | Test / Inspection | IN PROGRESS | Cell temperature measurement verified across cold and warm chambers from -20.0°C to +70.0°C with accuracy of ±0.6°C. Full low-temp (-40°C) and high-temp (+85°C) qualification pending chamber availability. | 09_Environmental_Thermal_Shock_Report.pdf | PARTIAL
REQ-AUT-004 | Continuous Current Sensing Dynamic Range & Accuracy | High-Voltage Battery | Test / Inspection | IN PROGRESS | Current sensor evaluated at discrete discharge test points of +100.0 A, +200.0 A, and +300.0 A with error <= 0.3%. Negative regen sweep and high current (> 300 A) characterization not yet performed. | 08_BMS_Functional_Safety_Validation_Report.pdf | PARTIAL
REQ-AUT-005 | Front-End ASIC High-Voltage Standoff Limit | High-Voltage Battery | Test / Inspection | COMPLETE | Absolute Maximum Ratings: Maximum continuous common-mode voltage rating is limited to 750.0 V DC. Operating above 750 V DC violates manufacturer warranty and risks junction punch-through. | 03_BMS_Cell_Supervisory_ASIC_Datasheet.pdf | FAIL
REQ-AUT-006 | Active Cell Balancing Balancing Current | High-Voltage Battery | Test / Inspection | COMPLETE | Thermal dissipation measurement on balancing circuitry: balancing current clamped to 120.0 mA max to prevent PCB hotspot exceeding 95°C. Does not meet 300 mA target. | 08_BMS_Functional_Safety_Validation_Report.pdf | FAIL
REQ-AUT-007 | Secondary Redundant Over-Temperature Hardware Cutoff | High-Voltage Battery | Test / Inspection | NOT STARTED | REQ-AUT-007; Secondary Analog Overtemperature Cutoff; Status: NOT STARTED - Hardware revision B pending. | 20_Master_Compliance_Verification_Matrix.xlsx | MISSING
REQ-AUT-008 | High-Voltage Isolation Loss Detection Response Time | High-Voltage Battery | Test / Inspection | NOT STARTED | Section 4.1: Isolation monitoring circuit layout reviewed. Isolation fault response timing test scheduled for Phase 3 validation. | 08_BMS_Functional_Safety_Validation_Report.pdf | MISSING
REQ-AUT-009 | Acoustic Gas Venting Detection Sensor Baseline | High-Voltage Battery | Test / Inspection | COMPLETE | Acoustic sensor baseline signal characterized in bench chamber. Sensor response demonstrated under generic ultrasonic pulse, but acoustic signature discrimination in vehicle enclosure cannot be confirmed without pack-level calibration. | 13_Thermal_Runaway_Venting_Validation_Report.pdf | REVIEW REQUIRED
REQ-AUT-010 | HV Interlock Loop (HVIL) Pulse Width Modulation Diagnostic | High-Voltage Battery | Test / Inspection | COMPLETE | HVIL signal generator is specified for 1 kHz PWM with 5 ms fault detector as described in architecture section 3.4. | 02_System_Architecture_Interface_Spec.pdf | REVIEW REQUIRED
REQ-AUT-011 | Inverter Phase Overcurrent Hardware Shutdown | Traction Inverter | Test / Inspection | COMPLETE | Short-circuit test with DESAT protection: peak current 680 A detected and all gates disabled in 1100 ns (1.1 µs). Verdict: PASS. | 08_BMS_Functional_Safety_Validation_Report.pdf | PASS
REQ-AUT-012 | DC-Link Capacitor Voltage Discharge Time | Traction Inverter | Test / Inspection | COMPLETE | Active discharge test: DC-link voltage decayed from 800 V to 42.5 V in 3.4 seconds. Verdict: PASS. | 08_BMS_Functional_Safety_Validation_Report.pdf | PASS
REQ-AUT-013 | Inverter Operating Efficiency Map | Traction Inverter | Test / Inspection | IN PROGRESS | Dynamometer efficiency test conducted at 4000 rpm from 100 Nm to 250 Nm showed efficiency of 98.1%. High-speed (10000 rpm) and low-torque (50 Nm) mapping remains pending dynamometer test slot. | 08_BMS_Functional_Safety_Validation_Report.pdf | PARTIAL
REQ-AUT-014 | Resolver Position Sensor Angle Tracking Jitter | Traction Inverter | Test / Inspection | IN PROGRESS | Resolver tracking error measured at +25°C ambient up to 15000 rpm was ±0.14 degrees. High temperature (+105°C) and max speed (20000 rpm) tests scheduled for next quarter. | 08_BMS_Functional_Safety_Validation_Report.pdf | PARTIAL
REQ-AUT-015 | SiC MOSFET Junction Temperature Derating Limit | Traction Inverter | Test / Inspection | COMPLETE | Absolute Maximum Ratings: Maximum allowable junction temperature Tj_max is 150.0°C. Continuous operation above 150°C causes irreversible gate oxide degradation. | 07_Silicon_Carbide_MOSFET_Datasheet.pdf | FAIL
REQ-AUT-016 | Phase Current Measurement Sensor Bandwidth | Traction Inverter | Test / Inspection | COMPLETE | Phase current sensor frequency response measured -3dB cutoff at 160.0 kHz. Bandwidth is insufficient for high-frequency PWM ripple observation. | 08_BMS_Functional_Safety_Validation_Report.pdf | FAIL
REQ-AUT-017 | Emergency Traction Torque Derating on CAN Loss | Traction Inverter | Test / Inspection | NOT STARTED | REQ-AUT-017; Traction Torque Derating on CAN Loss; Status: NOT STARTED - Motor dyno CAN fault injection pending. | 20_Master_Compliance_Verification_Matrix.xlsx | MISSING
REQ-AUT-018 | Inverter Coolant Flow Rate vs Thermal Resistance | Traction Inverter | Test / Inspection | NOT STARTED | REQ-AUT-018; Inverter Coolant Flow vs Thermal Resistance; Status: NOT STARTED - Thermal bench awaiting flow meter calibration. | 20_Master_Compliance_Verification_Matrix.xlsx | MISSING
REQ-AUT-019 | Space Vector PWM Harmonic Distortion (THD) | Traction Inverter | Test / Inspection | COMPLETE | MATLAB/Simulink power stage simulation predicts current THD of 2.4% under ideal switching parameters. | 13_Thermal_Runaway_Venting_Validation_Report.pdf | REVIEW REQUIRED
REQ-AUT-020 | Field Oriented Control (FOC) Flux Weakening Stability | Traction Inverter | Test / Inspection | COMPLETE | Section 5.2 defines the FOC flux weakening vector control block architecture and current loop equations. | 02_System_Architecture_Interface_Spec.pdf | REVIEW REQUIRED
REQ-AUT-021 | HV-to-LV DC-DC Output Voltage Regulation | Power Distribution | Test / Inspection | COMPLETE | Transient step load test: 10 A to 200 A transient caused 13.84 V output, recovered within 320 µs. Verdict: PASS. | 18_DC_DC_Converter_Efficiency_Test_Report.pdf | PASS
REQ-AUT-022 | DC-DC Converter Dielectric Withstand Isolation | Power Distribution | Test / Inspection | COMPLETE | Hipot test between HV and LV domains applied 3000 V AC rms for 60 s; measured leakage current was 0.38 mA. Verdict: PASS. | 18_DC_DC_Converter_Efficiency_Test_Report.pdf | PASS
REQ-AUT-023 | DC-DC Conversion Efficiency Across Load Profile | Power Distribution | Test / Inspection | IN PROGRESS | Efficiency measured at 1000 W (95.2%) and 2000 W (94.8%). Low power (300 W) and full power (3000 W) efficiency points not yet measured. | 18_DC_DC_Converter_Efficiency_Test_Report.pdf | PARTIAL
REQ-AUT-024 | 12V Output Voltage Ripple and Noise | Power Distribution | Test / Inspection | IN PROGRESS | Output ripple measured at 25°C ambient was 68.0 mVpp. Thermal chamber ripple measurements at -40°C and +85°C pending. | 18_DC_DC_Converter_Efficiency_Test_Report.pdf | PARTIAL
REQ-AUT-025 | Low-Voltage Output Continuous Current Rating | Power Distribution | Test / Inspection | COMPLETE | Maximum continuous rated LV current output is 180.0 A at 65°C ambient due to inductor thermal saturation limit. | 06_Traction_Inverter_IGBT_Module_Datasheet.pdf | FAIL
REQ-AUT-026 | HV Input Under-Voltage Lockout Threshold | Power Distribution | Test / Inspection | COMPLETE | Input voltage ramp test: DC-DC converter continued switching down to 290.0 V DC before tripping, failing the 350.0 V undervoltage threshold. | 18_DC_DC_Converter_Efficiency_Test_Report.pdf | FAIL
REQ-AUT-027 | Low-Voltage Reverse Polarity Protection | Power Distribution | Test / Inspection | NOT STARTED | REQ-AUT-027; LV Reverse Polarity Protection; Status: NOT STARTED - Destructive bench test scheduled. | 20_Master_Compliance_Verification_Matrix.xlsx | MISSING
REQ-AUT-028 | Over-Current Hiccup Mode Recovery Period | Power Distribution | Test / Inspection | NOT STARTED | REQ-AUT-028; Overcurrent Hiccup Mode Recovery; Status: NOT STARTED - Firmware short-circuit test pending. | 20_Master_Compliance_Verification_Matrix.xlsx | MISSING
REQ-AUT-029 | Conducted Voltage Transients Suppression (ISO 7637-2) | Power Distribution | Test / Inspection | COMPLETE | SPICE circuit simulation shows clamping TVS diode limits pulse 2a peak to 16.2 V. | 13_Thermal_Runaway_Venting_Validation_Report.pdf | REVIEW REQUIRED
REQ-AUT-030 | Pre-Charge Sequence Soft-Start Inrush Current | Power Distribution | Test / Inspection | COMPLETE | Section 4.3 defines the pre-charge resistor sizing (50 ohm) and soft-start timing diagram. | 02_System_Architecture_Interface_Spec.pdf | REVIEW REQUIRED
REQ-AUT-031 | Three-Phase AC Charging Power and Power Factor | Charging Systems | Test / Inspection | COMPLETE | Grid test at 400 V AC 3-phase delivered 11.05 kW with measured power factor of 0.992. Verdict: PASS. | 19_OnBoard_Charger_AC_Validation_Report.pdf | PASS
REQ-AUT-032 | Control Pilot (CP) Duty Cycle Detection Tolerance | Charging Systems | Test / Inspection | COMPLETE | Control pilot duty cycle sweep from 10.0% to 90.0% measured with maximum error of ±0.22% duty cycle. Verdict: PASS. | 19_OnBoard_Charger_AC_Validation_Report.pdf | PASS
REQ-AUT-033 | AC Input Voltage Operating Range & Frequency Tolerance | Charging Systems | Test / Inspection | IN PROGRESS | Tested at 230 V AC / 50 Hz and 120 V AC / 60 Hz. Low-line voltage limit (85 V) and frequency margin (47 Hz, 63 Hz) tests pending. | 19_OnBoard_Charger_AC_Validation_Report.pdf | PARTIAL
REQ-AUT-034 | V2L (Vehicle-to-Load) Bidirectional Output Voltage & Distortion | Charging Systems | Test / Inspection | IN PROGRESS | V2L evaluated with 1.8 kW resistive heater: output 230.4 V, THD 1.8%. Inductive load testing (3.6 kW motor load) remains pending. | 19_OnBoard_Charger_AC_Validation_Report.pdf | PARTIAL
REQ-AUT-035 | Maximum AC Input Leakage Current to Earth | Charging Systems | Test / Inspection | COMPLETE | Earth leakage current test: measured touch leakage current was 5.2 mA rms due to Y-capacitor filter sizing, exceeding 3.5 mA limit. | 19_OnBoard_Charger_AC_Validation_Report.pdf | FAIL
REQ-AUT-036 | Charging Inlet Thermal Sensor Shutdown Limit | Charging Systems | Test / Inspection | COMPLETE | Inlet temperature override test: controller throttled at 95.0°C and did not terminate charging until 108.0°C. | 19_OnBoard_Charger_AC_Validation_Report.pdf | FAIL
REQ-AUT-037 | DC Fast Charging CCS Combo 2 Isolation Check Sequence | Charging Systems | Test / Inspection | NOT STARTED | REQ-AUT-037; DC Fast Charging CCS Precharge Isolation; Status: NOT STARTED - DC fast charge emulator awaiting firmware update. | 20_Master_Compliance_Verification_Matrix.xlsx | MISSING
REQ-AUT-038 | Proximity Pilot (PP) Resistor Value Discrimination | Charging Systems | Test / Inspection | NOT STARTED | REQ-AUT-038; Proximity Pilot Resistor Discrimination; Status: NOT STARTED - Cable resistance fixture pending. | 20_Master_Compliance_Verification_Matrix.xlsx | MISSING
REQ-AUT-039 | Grid Surge Transient Protection (IEC 61000-4-5) | Charging Systems | Test / Inspection | COMPLETE | Transient surge suppression modeled in LTspice with MOV + gas tube surge arrestor. | 13_Thermal_Runaway_Venting_Validation_Report.pdf | REVIEW REQUIRED
REQ-AUT-040 | Smart Grid ISO 15118-20 TLS Handshake Timing | Charging Systems | Test / Inspection | COMPLETE | Section 6.1 specifies the HomePlug GreenPHY architecture and TLS 1.3 cipher suite requirements. | 02_System_Architecture_Interface_Spec.pdf | REVIEW REQUIRED
REQ-AUT-041 | Battery Pack Coolant Chiller Temperature Regulation | Thermal Management | Test / Inspection | COMPLETE | Thermal bench test: inlet coolant temperature stabilized at 25.4°C under 5.2 kW steady thermal dissipation. Verdict: PASS. | 13_Thermal_Runaway_Venting_Validation_Report.pdf | PASS
REQ-AUT-042 | HV Electric AC Compressor Speed Control | Thermal Management | Test / Inspection | COMPLETE | Compressor speed sweep from 1000 rpm to 8500 rpm verified; maximum observed speed error was 28 rpm. Verdict: PASS. | 13_Thermal_Runaway_Venting_Validation_Report.pdf | PASS
REQ-AUT-043 | Cabin Heat Pump Heating Capacity at Low Ambient | Thermal Management | Test / Inspection | IN PROGRESS | Heat pump tested at 0°C and -5°C ambient delivering 5.1 kW and 4.8 kW respectively. Extreme cold chamber test at -15.0°C pending. | 13_Thermal_Runaway_Venting_Validation_Report.pdf | PARTIAL
REQ-AUT-044 | Electronic Expansion Valve (EXV) Positioning Steps | Thermal Management | Test / Inspection | IN PROGRESS | EXV positioning verified at +25°C ambient across full 500 steps. Cold step validation at -30°C scheduled for next test run. | 13_Thermal_Runaway_Venting_Validation_Report.pdf | PARTIAL
REQ-AUT-045 | Coolant Circuit Maximum Operating Pressure | Thermal Management | Test / Inspection | COMPLETE | Component Maximum Pressure Rating: Maximum continuous rated pressure for 3-way coolant valve is 1.80 bar. Pressures above 1.8 bar risk seal deformation. | 04_High_Voltage_Contactor_Datasheet.pdf | FAIL
REQ-AUT-046 | PTC Heater Ramp Rate to Rated Power | Thermal Management | Test / Inspection | COMPLETE | PTC heater step response test: measured 32.4 seconds to reach 90% power (5.4 kW) due to soft-start inrush current limiting. | 13_Thermal_Runaway_Venting_Validation_Report.pdf | FAIL
REQ-AUT-047 | Coolant Degassing and Air Bubble Detection | Thermal Management | Test / Inspection | NOT STARTED | REQ-AUT-047; Coolant Degassing Air Bubble Purge; Status: NOT STARTED - Optical bubble sensor integration pending. | 20_Master_Compliance_Verification_Matrix.xlsx | MISSING
REQ-AUT-048 | Refrigerant Pressure Relief Valve Burst Pressure | Thermal Management | Test / Inspection | NOT STARTED | REQ-AUT-048; Refrigerant Relief Valve Burst Pressure; Status: NOT STARTED - Destructive pressure test scheduled. | 20_Master_Compliance_Verification_Matrix.xlsx | MISSING
REQ-AUT-049 | Cabin Thermal Comfort Model (PMV/PPD) | Thermal Management | Test / Inspection | COMPLETE | CFD thermal cabin comfort modeling demonstrates PMV of +0.2 under simulated 22°C ambient. | 13_Thermal_Runaway_Venting_Validation_Report.pdf | REVIEW REQUIRED
REQ-AUT-050 | Electric Water Pump Dry-Run Protection Response | Thermal Management | Test / Inspection | COMPLETE | Section 7.4 describes water pump LIN diagnostic messages and dry-run fault detection algorithm. | 02_System_Architecture_Interface_Spec.pdf | REVIEW REQUIRED
REQ-AUT-051 | CAN-FD Dual Bitrate Transmission Rate | In-Vehicle Networking | Test / Inspection | COMPLETE | Oscilloscope bus timing analysis confirmed 500.0 kbps arbitration and 5.00 Mbps data phase with 75.0% sample point. Verdict: PASS. | 14_CAN_FD_Network_Timing_Test_Report.pdf | PASS
REQ-AUT-052 | CAN Bus-Off Recovery State Machine Timing | In-Vehicle Networking | Test / Inspection | COMPLETE | Fault injection bus-off test: node resumed transmission on CAN bus at 94.6 ms following error frame burst. Verdict: PASS. | 14_CAN_FD_Network_Timing_Test_Report.pdf | PASS
REQ-AUT-053 | CAN-FD End-to-End (E2E) Profile 01 Checksum & Counter | In-Vehicle Networking | Test / Inspection | IN PROGRESS | E2E Profile 01 verified on BMS status messages (IDs 0x100 to 0x108). Inverter and DC-DC message IDs (0x109 to 0x110) E2E verification pending. | 14_CAN_FD_Network_Timing_Test_Report.pdf | PARTIAL
REQ-AUT-054 | 100Base-T1 Automotive Ethernet Bit Error Rate (BER) | In-Vehicle Networking | Test / Inspection | IN PROGRESS | Ethernet BER tested over 5 meters cable length showed zero bit errors (BER < 10^-11). Full 15-meter harness length test pending harness fabrication. | 15_Automotive_Ethernet_100Base_T1_Report.pdf | PARTIAL
REQ-AUT-055 | CAN Transceiver Common Mode Bus Voltage Tolerance | In-Vehicle Networking | Test / Inspection | COMPLETE | Absolute Maximum Ratings: Maximum continuous common-mode voltage range is -7.0 V to +7.0 V DC. Operation beyond ±7 V causes bit decoding errors. | 03_BMS_Cell_Supervisory_ASIC_Datasheet.pdf | FAIL
REQ-AUT-056 | Ethernet SOME/IP Message Transmission Latency | In-Vehicle Networking | Test / Inspection | COMPLETE | Ethernet traffic analysis under 70% network load: measured SOME/IP packet latency was 2.8 ms due to queue buffer contention. | 15_Automotive_Ethernet_100Base_T1_Report.pdf | FAIL
REQ-AUT-057 | LIN Bus Sleep Mode Quiescent Current Consumption | In-Vehicle Networking | Test / Inspection | NOT STARTED | REQ-AUT-057; LIN Slave Quiescent Sleep Current; Status: NOT STARTED - Low-power sleep current bench pending. | 20_Master_Compliance_Verification_Matrix.xlsx | MISSING
REQ-AUT-058 | CAN Network Management (Autosar NM) Ring Synchronization | In-Vehicle Networking | Test / Inspection | NOT STARTED | REQ-AUT-058; AUTOSAR Network Management Sleep Ring; Status: NOT STARTED - Multi-ECU test rack setup in progress. | 20_Master_Compliance_Verification_Matrix.xlsx | MISSING
REQ-AUT-059 | gPTP (IEEE 802.1AS) Time Synchronization Jitter | In-Vehicle Networking | Test / Inspection | COMPLETE | Network simulation in OMNeT++ predicts clock drift synchronization within 420 ns. | 15_Automotive_Ethernet_100Base_T1_Report.pdf | REVIEW REQUIRED
REQ-AUT-060 | TCP/IP Stack Socket Resource Allocation | In-Vehicle Networking | Test / Inspection | COMPLETE | Section 8.1 defines the static socket buffer allocation tables in AUTOSAR BswM configuration. | 02_System_Architecture_Interface_Spec.pdf | REVIEW REQUIRED
REQ-AUT-061 | UDS Diagnostic Session Control (0x10) P2 Server Timing | Diagnostics & Bootloader | Test / Inspection | COMPLETE | UDS Service 0x10 diagnostic timing test: measured P2 server response time across 100 requests was 18.4 ms max. Verdict: PASS. | 16_UDS_Diagnostics_Security_Access_Report.pdf | PASS
REQ-AUT-062 | Diagnostic Fault Code (DTC) Snapshot Freeze Frame Storage | Diagnostics & Bootloader | Test / Inspection | COMPLETE | DTC snapshot validation test: freeze frame written to NVRAM in 12.8 ms with complete mandatory sensor records. Verdict: PASS. | 16_UDS_Diagnostics_Security_Access_Report.pdf | PASS
REQ-AUT-063 | UDS Security Access (Service 0x27) Seed-Key Authentication | Diagnostics & Bootloader | Test / Inspection | IN PROGRESS | Level 0x01 Reprogramming security access validated with ECDSA-256. Level 0x03 Engineering calibration access security test pending implementation. | 16_UDS_Diagnostics_Security_Access_Report.pdf | PARTIAL
REQ-AUT-064 | Firmware OTA Dual-Bank A/B Rollback Recovery | Diagnostics & Bootloader | Test / Inspection | IN PROGRESS | Corrupted image injected into Bank B; bootloader detected CRC mismatch and initiated rollback in 1.4 seconds. Golden image boot verification scheduled. | 16_UDS_Diagnostics_Security_Access_Report.pdf | PARTIAL
REQ-AUT-065 | Diagnostic Service Port Authentication Requirement | Diagnostics & Bootloader | Test / Inspection | COMPLETE | Section 3.2: Diagnostic port configuration revealed Service 0x23 ReadMemoryByAddress is configured with open access with no login or authentication required. | 16_UDS_Diagnostics_Security_Access_Report.pdf | FAIL
REQ-AUT-066 | ECU Flash Reprogramming Erase & Write Throughput | Diagnostics & Bootloader | Test / Inspection | COMPLETE | Flash throughput benchmark: measured write speed was 38.5 kB/s due to internal flash block erase wait states. | 16_UDS_Diagnostics_Security_Access_Report.pdf | FAIL
REQ-AUT-067 | RoutineControl (0x31) Actuator Self-Test Timeout | Diagnostics & Bootloader | Test / Inspection | NOT STARTED | REQ-AUT-067; RoutineControl 0x31 Contactor Welded Test; Status: NOT STARTED - RoutineControl self-test script pending. | 20_Master_Compliance_Verification_Matrix.xlsx | MISSING
REQ-AUT-068 | UDS TesterPresent (0x3E) S3 Timer Expiration Recovery | Diagnostics & Bootloader | Test / Inspection | NOT STARTED | REQ-AUT-068; TesterPresent S3 Timeout Session Recovery; Status: NOT STARTED - Diagnostic timer test pending. | 20_Master_Compliance_Verification_Matrix.xlsx | MISSING
REQ-AUT-069 | Non-Volatile Memory (NVRAM) Wear-Leveling Endurance | Diagnostics & Bootloader | Test / Inspection | COMPLETE | NVRAM endurance calculation model estimates 125,000 cycles based on Flash memory manufacturer cell fatigue curve. | 13_Thermal_Runaway_Venting_Validation_Report.pdf | REVIEW REQUIRED
REQ-AUT-070 | Diagnostic Response On Sub-Function Not Supported (NRC 0x12) | Diagnostics & Bootloader | Test / Inspection | COMPLETE | Section 9.2 specifies negative response code handling tables for diagnostic stack. | 02_System_Architecture_Interface_Spec.pdf | REVIEW REQUIRED
REQ-AUT-071 | External Window Watchdog Challenge-Response Timeout | Functional Safety | Test / Inspection | COMPLETE | Watchdog timing verification: SPI challenge-response verified at 15.2 ms interval. Forced late response triggered hardware reset in 18.1 ms. Verdict: PASS. | 08_BMS_Functional_Safety_Validation_Report.pdf | PASS
REQ-AUT-072 | Core Voltage Brownout Detection & Safe State Transition | Functional Safety | Test / Inspection | COMPLETE | Brownout injection test: Vcore reduced to 2.94 V triggered PMIC hard RESET in 2.1 µs. Verdict: PASS. | 08_BMS_Functional_Safety_Validation_Report.pdf | PASS
REQ-AUT-073 | Lockstep Dual-Core MCU Redundancy Fault Injection | Functional Safety | Test / Inspection | IN PROGRESS | Lockstep error injection on Core 0 ALU registers triggered safety alarm in 1 clock cycle. Core 1 memory bus fault injection test pending. | 08_BMS_Functional_Safety_Validation_Report.pdf | PARTIAL
REQ-AUT-074 | Safety-Related ADC Redundant Cross-Check Discrepancy | Functional Safety | Test / Inspection | IN PROGRESS | Cross-check algorithm verified at room temperature with 2.0% injected delta, fault asserted at 52 ms. Cold temperature (-40°C) cross-check pending. | 08_BMS_Functional_Safety_Validation_Report.pdf | PARTIAL
REQ-AUT-075 | Fault Reaction Time to Safe State for Overcurrent | Functional Safety | Test / Inspection | COMPLETE | Fault injection test: measured total elapsed time from overcurrent trigger to STO state transition was 24.5 ms due to filter debounce delay. | 08_BMS_Functional_Safety_Validation_Report.pdf | FAIL
REQ-AUT-076 | Microcontroller Flash Memory ECC Single-Bit Correction | Functional Safety | Test / Inspection | COMPLETE | Memory fault injection: double-bit flash error triggered standard exception handler in 450 ns instead of required 100 ns NMI. | 08_BMS_Functional_Safety_Validation_Report.pdf | FAIL
REQ-AUT-077 | Plausibility Check on Dual Throttle Pedal Position Sensors | Functional Safety | Test / Inspection | NOT STARTED | REQ-AUT-077; Dual Throttle Pedal Plausibility Check; Status: NOT STARTED - Throttle pedal sensor rig pending. | 20_Master_Compliance_Verification_Matrix.xlsx | MISSING
REQ-AUT-078 | Hardware Built-In Self-Test (BIST) Startup Execution Time | Functional Safety | Test / Inspection | NOT STARTED | REQ-AUT-078; Hardware Built-In Self-Test (BIST) Execution; Status: NOT STARTED - BIST startup profiling pending. | 20_Master_Compliance_Verification_Matrix.xlsx | MISSING
REQ-AUT-079 | Diagnostic Coverage (DC) for ASIL-D ISO 26262 Compliance | Functional Safety | Test / Inspection | COMPLETE | FMEDA quantitative calculation report indicates theoretical SPFM of 99.4% and LFM of 91.2%. | 08_BMS_Functional_Safety_Validation_Report.pdf | REVIEW REQUIRED
REQ-AUT-080 | Clock Monitor Oscillator Frequency Drift Detection | Functional Safety | Test / Inspection | COMPLETE | Section 10.1 defines the clock supervisor hardware architecture and backup oscillator configuration. | 02_System_Architecture_Interface_Spec.pdf | REVIEW REQUIRED
REQ-AUT-081 | Secure Boot Cryptographic Verification Latency | Cybersecurity | Test / Inspection | COMPLETE | Secure boot benchmark: RSA-3072 signature verification completed in 112.4 ms with valid public key. Verdict: PASS. | 17_Cybersecurity_HSM_SecOC_Validation_Report.pdf | PASS
REQ-AUT-082 | AUTOSAR SecOC AES-128 CMAC Generation Time | Cybersecurity | Test / Inspection | COMPLETE | SecOC hardware acceleration benchmark: measured AES-128 CMAC generation time was 28.5 µs per message. Verdict: PASS. | 17_Cybersecurity_HSM_SecOC_Validation_Report.pdf | PASS
REQ-AUT-083 | Cryptographic Key Storage Hardware Isolation | Cybersecurity | Test / Inspection | IN PROGRESS | AES symmetric root keys verified inside HSM secure storage. Asymmetric ECC private key migration to secure keystore pending firmware v2.1. | 17_Cybersecurity_HSM_SecOC_Validation_Report.pdf | PARTIAL
REQ-AUT-084 | Cybersecurity Intrusion Detection System (IDS) Rate Limiting | Cybersecurity | Test / Inspection | IN PROGRESS | IDS rate limiter evaluated on CAN 1 (Powertrain) and CAN 2 (Body); blocked injection in 32.0 ms. CAN 3 (Chassis) and CAN 4 (Infotainment) testing pending. | 17_Cybersecurity_HSM_SecOC_Validation_Report.pdf | PARTIAL
REQ-AUT-085 | Diagnostic JTAG / Debug Port Permanent Locking | Cybersecurity | Test / Inspection | COMPLETE | Hardware inspection: JTAG port pins remain accessible with debugging enabled on production sample lot #3 due to unblown e-fuses. | 17_Cybersecurity_HSM_SecOC_Validation_Report.pdf | FAIL
REQ-AUT-086 | True Random Number Generator (TRNG) Entropy Throughput | Cybersecurity | Test / Inspection | COMPLETE | NIST SP 800-22 random number test suite: measured TRNG output rate was 140.0 kbps, failing the 500.0 kbps throughput requirement. | 17_Cybersecurity_HSM_SecOC_Validation_Report.pdf | FAIL
REQ-AUT-087 | Diagnostic Certificate Revocation List (CRL) Verification | Cybersecurity | Test / Inspection | NOT STARTED | REQ-AUT-087; Certificate Revocation List (CRL) Verification; Status: NOT STARTED - PKI certificate authority server integration pending. | 20_Master_Compliance_Verification_Matrix.xlsx | MISSING
REQ-AUT-088 | Side-Channel Attack DPA / SPA Resistance | Cybersecurity | Test / Inspection | NOT STARTED | REQ-AUT-088; Side-Channel DPA / SPA Resistance; Status: NOT STARTED - Side-channel analysis lab test scheduled. | 20_Master_Compliance_Verification_Matrix.xlsx | MISSING
REQ-AUT-089 | Threat Analysis and Risk Assessment (TARA) Residual Risk Score | Cybersecurity | Test / Inspection | COMPLETE | TARA analysis report section 4 evaluates 42 threat vectors and assigns theoretical CAL ratings. | 08_BMS_Functional_Safety_Validation_Report.pdf | REVIEW REQUIRED
REQ-AUT-090 | Secure Logging of Security Events (SecEvent) | Cybersecurity | Test / Inspection | COMPLETE | Section 11.3 describes the secure logging event format and flash partition layout. | 02_System_Architecture_Interface_Spec.pdf | REVIEW REQUIRED
REQ-AUT-091 | CISPR 25 Class 4 Radiated Emissions Margin | Environmental & EMC | Test / Inspection | COMPLETE | Semi-anechoic chamber radiated emissions sweep 150 kHz–2.5 GHz: all frequency peaks remained >= 6.4 dB below CISPR 25 Class 4 limit. Verdict: PASS. | 11_EMC_Radiated_Immunity_Test_Report.pdf | PASS
REQ-AUT-092 | ISO 16750-2 Jump Start Overvoltage Withstand | Environmental & EMC | Test / Inspection | COMPLETE | Jump start simulation: 26.0 V DC applied for 60.0 seconds; no thermal runaway or parametric drift observed. Verdict: PASS. | 12_Electrical_Transient_Overvoltage_Report.pdf | PASS
REQ-AUT-093 | 3-Axis Random Vibration Endurance Profile (ISO 16750-3) | Environmental & EMC | Test / Inspection | IN PROGRESS | Random vibration test completed on X-axis (8.0 h) and Y-axis (8.0 h) at 2.50 g RMS with zero mechanical failure. Z-axis vibration run pending shaker maintenance. | 10_Mechanical_Vibration_Shock_Report.pdf | PARTIAL
REQ-AUT-094 | Thermal Shock Cycling With Fast Transition (-40°C to +85°C) | Environmental & EMC | Test / Inspection | IN PROGRESS | Thermal shock chamber test completed 250 cycles of 500 total cycles with zero solder joint cracking. Remaining 250 cycles currently in progress in chamber #2. | 09_Environmental_Thermal_Shock_Report.pdf | PARTIAL
REQ-AUT-095 | IP Ingress Protection Enclosure Rating | Environmental & EMC | Test / Inspection | COMPLETE | Ingress protection test: housing passed IP6X dust test, but water ingress of 4.2 mL observed during 1m submersion test due to connector gasket leakage. Rated as IP65 only. | 10_Mechanical_Vibration_Shock_Report.pdf | FAIL
REQ-AUT-096 | ISO 7637-2 Pulse 3a / 3b Fast Transient Immunity | Environmental & EMC | Test / Inspection | COMPLETE | Electrical transient test: application of Pulse 3a (-150 V) caused microcontroller reset (Class C behavior), violating Class A requirement. | 12_Electrical_Transient_Overvoltage_Report.pdf | FAIL
REQ-AUT-097 | Salt Spray Corrosion Resistance (ISO 9227) | Environmental & EMC | Test / Inspection | NOT STARTED | REQ-AUT-097; Salt Spray Corrosion Resistance; Status: NOT STARTED - Salt spray chamber testing scheduled. | 20_Master_Compliance_Verification_Matrix.xlsx | MISSING
REQ-AUT-098 | High-Temperature Operating Life (HTOL) Reliability Test | Environmental & EMC | Test / Inspection | NOT STARTED | REQ-AUT-098; High-Temperature Operating Life (HTOL); Status: NOT STARTED - HTOL burn-in chamber test pending. | 20_Master_Compliance_Verification_Matrix.xlsx | MISSING
REQ-AUT-099 | Damp Heat Steady State Cyclic Humidity (ISO 16750-4) | Environmental & EMC | Test / Inspection | COMPLETE | Conformal coating moisture permeation model calculates insulation resistance > 100 MΩ under 95% RH. | 13_Thermal_Runaway_Venting_Validation_Report.pdf | REVIEW REQUIRED
REQ-AUT-100 | Mechanical Shock Half-Sine Pulse Profile | Environmental & EMC | Test / Inspection | COMPLETE | Section 12.1 specifies mechanical shock test parameters and fixture mounting details per ISO 16750-3. | 02_System_Architecture_Interface_Spec.pdf | REVIEW REQUIRED